# Question 3 :

From the SCMS requirements document, identify all the **additional details and clarifications** needed to develop a complete Project Plan and Work Breakdown Structure (WBS).

Please include the information required under:

- Scope boundaries and assumptions

- Team and resource requirements

- Technical architecture and environment setup

- Integration points and external dependencies

- Data migration and quality validation

- Acceptance criteria and KPIs

- Deployment and go-live plan

- Risk management and contingency planning

For each missing detail, specify:

1. What information is missing

2. Why it’s important for planning or estimation

3. What specific questions should be asked to gather that information

[Attach or paste your “Requirements Document_ State Childcare Management System (SCMS).pdf” content here.]

# Answer :

I'll create a comprehensive document identifying all the additional details needed for a complete Project Plan and WBS.Excellent! I've created a comprehensive document identifying all the missing planning details needed for a complete Project Plan and WBS.

View your Project Planning Requirements document

## Document Overview

The analysis identifies 75 critical planning questions organized into eight categories. Each question includes what's missing, why it matters for planning, and what specific questions should be asked.

### 1. Scope Boundaries and Assumptions (10 questions)

- Geographic boundaries - Which counties/regions? Statewide or pilot?

- User population size - How many families, providers, caseworkers?

- Transaction volumes - Applications/year, payments/month, attendance records/day?

- What's OUT of scope - Background checks? Co-payment collection? Adjacent programs?

- System replacement vs new - What exists today? Greenfield or migration?

- MVP definition - What's minimum for go-live? What can be deferred?

- Service level expectations - 24/7 or business hours? Acceptable downtime?

- Multi-language requirements - Spanish required? What % LEP population?

- Historical data requirements - How many years to migrate?

- Provider onboarding scope - Mass conversion or gradual enrollment?

### 2. Team and Resource Requirements (8 questions)

- State team composition - How many FTEs? What skills in-house?

- Decision authority - Who approves requirements, scope changes, budget?

- SME availability - Hours per week? Who are backups?

- Vendor vs state responsibilities - Who does development, infrastructure, training?

- Technical staff skills - Can state maintain post-launch? Training needed?

- Procurement constraints - Sole-source or competitive? Contract vehicles?

- Third-party contractors - Other vendors involved? Who provides hosting?

- Staff turnover planning - Typical turnover rate? Knowledge retention strategy?

### 3. Technical Architecture and Environment Setup (10 questions)

- Technology stack mandates - Required databases, frameworks, blacklisted tech?

- Hosting environment - State data center or cloud? Which provider?

- Network and connectivity - Topology? Bandwidth? Firewall rules?

- Security requirements - Which framework (NIST 800-53)? Authorization level?

- Environment strategy - How many environments? Who provides?

- Disaster recovery location - Required? Distance from primary?

- Development tools - Source control, CI/CD, testing tools required?

- Performance testing - Load testing scope? Tools? Acceptance criteria?

- Third-party components - Can COTS be used? Open source allowed?

- Monitoring and observability - Monitoring tools? Metrics? Alerting?

### 4. Integration Points and External Dependencies (10 questions)

- Existing systems inventory - What systems currently support program?

- Integration patterns - Real-time vs batch? APIs available?

- Authentication and SSO - What identity provider? Protocols supported?

- Financial system details - Which system? Version? APIs available?

- Income verification approach - Access to Work Number? State wage databases?

- Background check integration - System used? Integration required?

- Licensing system integration - Can license data be integrated?

- External data dependencies - Third-party services needed? Costs?

- Master data management - Authoritative source for provider/child data?

- Interface SLAs - Response time requirements? Uptime expected?

### 5. Data Migration and Quality Validation (10 questions)

- Legacy data sources - What systems contain data? File formats?

- Data migration scope - Which entities? How much history?

- Data quality baseline - Known issues? Duplicate percentage?

- Data mapping documentation - Field mappings? Transformations needed?

- Data validation rules - What error rate acceptable? Reconciliation process?

- Data migration timing - When does migration occur? Cutover window?

- Data conversion tools - ETL tools available? Custom scripts?

- Data stewardship - Who makes data correction decisions?

- Fallback plan - Rollback plan if migration fails?

- Document migration - How many documents? File types? Storage approach?

### 6. Acceptance Criteria and KPIs (9 questions)

- Phase completion criteria - What deliverables mark end of each phase?

- UAT approach - Who participates? Duration? Pass criteria?

- Test data requirements - How created? How many test cases?

- Performance benchmarks - Specific targets by transaction type?

- Go-live readiness criteria - What must be 100% complete?

- Success metrics post-launch - Which KPIs? Targets? When measured?

- Warranty period expectations - Duration? Coverage? Response times?

- Training completion criteria - What % must be trained? Assessments?

- Data migration acceptance - Reconciliation reports? Acceptable discrepancy?

### 7. Deployment and Go-Live Plan (10 questions)

- Go-live date and milestones - Target date? Is it flexible? What drives it?

- Deployment approach - Big bang or phased? Pilot strategy?

- Cutover procedures - Cutover window? Sequence? Planned downtime?

- Parallel run requirements - Required? How long? Reconciliation approach?

- Deployment prerequisites - What must be ready? Pre-launch checklist?

- Hypercare period plan - Duration? Elevated support staffing?

- User provisioning logistics - How are initial accounts created? Timeline?

- Data cutover strategy - How are in-flight cases handled? Data freeze?

- Rollback plan - What triggers rollback? Procedure? Recovery approach?

- Communication plan - What communications? When? To whom?

### 8. Risk Management and Contingency Planning (10 questions)

- Risk register - What technical, schedule, vendor, political risks?

- Risk mitigation strategies - Mitigation and contingency for each risk?

- Dependency management - What external approvals, procurements needed?

- Resource constraints - When are SMEs unavailable? Competing priorities?

- Change management risks - Anticipated resistance? Change champions?

- Technical risks - Technical unknowns? What needs POC?

- Regulatory and compliance risks - What approvals required? Timeline?

- Budget overrun risks - Cost risk factors? Contingency reserve?

- Schedule risks - What has schedule uncertainty? Critical path float?

- Contingency plans - Plan B if vendor fails, go-live delayed, budget cut?

## Key Findings

Critical Gap: Complete absence of quantitative information makes accurate estimation impossible. User counts, transaction volumes, and data quantities are essential for infrastructure sizing, license costs, and capacity planning.

Planning Timeline Impact: Without this information, cost estimates will vary by 100-200%, schedules lack basis, and vendor proposals will be incomparable.

Recommended Solution: Conduct a 5-day planning workshop with all key stakeholders to systematically answer these 75 questions before proceeding with RFP development or vendor selection.

## Workshop Deliverables

The document includes a detailed recommendation for a structured planning workshop that would produce:

- Quantitative scope parameters document

- RACI matrix for roles and responsibilities

- Technical standards and constraints document

- Integration requirements specification

- Data migration scope and approach

- Acceptance criteria and KPI definitions

- Deployment strategy and timeline constraints

- Risk register with mitigation strategies

This comprehensive planning foundation is essential before moving to detailed project planning or vendor engagement.

Refer to the document: SCMS_Project_Planning_Requirements.docx