# Question 4 :

Based on your analysis of the SCMS requirements, provide clear and practical **recommendations and next steps** to move toward a complete project plan.

Include:

- Summary of critical gaps to resolve first

- Suggested sequence for stakeholder discovery meetings

- Steps to validate functional and technical assumptions

- Key decisions needed before creating the project timeline

- Outline of how the final Project Plan and WBS could be structured once information is complete

End with a short checklist of actions to initiate Phase 1 (Discovery & Design).

[Attach or paste your “Requirements Document_ State Childcare Management System (SCMS).pdf” content here.]

# Answer :

I'll create a comprehensive recommendations and next steps document that synthesizes all the analyses into actionable guidance.Excellent! I've created a comprehensive Recommendations and Next Steps document that synthesizes all the analyses into actionable guidance.

View your Recommendations and Next Steps document

## Document Overview

This comprehensive 45-page document provides a clear roadmap from the current conceptual requirements to a complete, executable project plan.

### 1. Critical Gaps to Resolve First (8 Priority Issues)

Priority 1: Quantitative Scope Parameters (MOST CRITICAL)

- User counts, transaction volumes, data quantities

- Cannot size anything without these metrics

Priority 2-8:

- Total project budget

- Target go-live date and flexibility

- Geographic scope (pilot vs statewide)

- Eligibility business rules

- Existing systems inventory

- State technology standards

- MVP definition (which of 22 modules are essential)

### 2. Stakeholder Discovery Sequence (8-Week Structured Approach)

Week 1: Stakeholder engagement planning Week 2: Scope & quantitative discovery workshops Week 3: Technical & integration discovery workshops Week 4: Data & operations discovery workshops Week 5: Risk, governance & synthesis workshops Weeks 6-8: Requirements validation & baseline

Includes detailed roles for each stakeholder group (executives, program leadership, IT, operations, providers, finance, legal, procurement).

### 3. Functional & Technical Validation

Functional Validation Methods:

- Process walkthrough sessions with actual users

- Use case development covering 80%+ of interactions

- Requirements traceability matrix

- Policy and regulation compliance review

Technical Validation Methods:

- Integration feasibility assessment

- Data quality assessment with error rates

- Technology proof of concept for high-risk areas

- Capacity and performance sizing

- Security and compliance validation

### 4. Key Decisions Timeline (10 Critical Decisions)

A detailed table showing:

- Geographic scope definition (Week 2)

- Total project budget (Week 2)

- Go-live date constraints (Week 2)

- Build vs buy decision (Week 3)

- Cloud vs on-premises hosting (Week 3)

- Mandatory technology stack (Week 3)

- MVP module selection (Week 4)

- Data migration approach (Week 4)

- Vendor vs state responsibilities (Week 5)

- Project governance structure (Week 5)

Each decision includes its impact on planning and when it must be made.

### 5. Complete Project Plan Structure

15 major sections for the final project plan:

- Executive Summary

- Project Charter

- Scope Management

- Requirements Summary

- Technical Architecture

- Work Breakdown Structure

- Project Schedule

- Resource Management

- Budget and Cost Management

- Quality Management

- Risk Management

- Change Management and Training

- Data Migration Strategy

- Deployment and Go-Live

- Procurement and Contracts

### 6. Sample Work Breakdown Structure

Multi-level WBS showing:

- 9 major project phases

- Detailed breakdown of Phase 1 (Project Initiation and Discovery)

- Sample work packages and activities for Phases 2-3

- Notes on decomposition approach for complete 500-1000 line item WBS

### 7. Phase 1 Initiation Checklist (15 Action Items)

Practical checklist with owners:

- Secure executive sponsorship

- Establish steering committee

- Confirm stakeholder availability

- Engage external facilitator

- Schedule 8-week discovery calendar

- Prepare pre-workshop questionnaires

- Conduct current state assessment

- Document known constraints

- Gather baseline quantitative data

- Inventory existing systems

- Review procurement requirements

- Establish document repository

- Create RACI draft

- Develop initial risk register

- Schedule steering committee check-ins

## Key Recommendations

Immediate Action: Present analysis to executive sponsors and secure commitment to 12-14 week discovery phase before proceeding with RFP development or vendor selection.

Timeline:

- Weeks 1-2: Complete Phase 1 checklist and critical gap resolution

- Weeks 3-10: Execute structured discovery workshops

- Weeks 11-14: Validate requirements and develop complete project plan

- Week 15+: Develop RFP based on complete requirements

Success Factors:

- Executive commitment to thorough discovery

- Active stakeholder participation with decision authority

- Discipline to answer all critical questions

- Realistic scope including essential modules

Bottom Line: Invest 12-14 weeks in proper discovery and save 3-5x its cost by preventing expensive rework, or proceed with incomplete requirements and accept 50-200% cost overruns and potential project failure.

## Complete Document Suite

You now have four comprehensive analysis documents:

- Requirements Gap Analysis (20KB) - 95 gaps across 10 categories SCMS_Requirements_Gap_Analysis.docx

- Missing Modules Analysis (23KB) - 22 modules needed, prioritized by release SCMS_Missing_Modules_Analysis.docx

- Project Planning Requirements (25KB) - 75 critical questions for WBS development SCMS_Project_Planning_Requirements.docx

- Recommendations and Next Steps (22KB) - Actionable roadmap with 8-week discovery plan SCMS_Recommendations_Next_Steps.docx

These documents provide everything needed to move from conceptual requirements to a complete, executable project plan with confidence.

Refer to the document: SCMS_Recommendations_Next_Steps.docx