# SCMS MVP Implementation Plan

## Case Management System - First Release

Project: State Childcare Management System (SCMS) - MVP
Version: 1.0
Date: November 8, 2025
Planning Period: 18 Weeks
Team Size: 8-10 people
Estimated Budget: $600K - $800K

## 📋 EXECUTIVE SUMMARY

### MVP Scope

Build an "Application to Approval System" that enables:

- Parents to apply for childcare assistance online

- State caseworkers to review and approve/reject applications

- Automated eligibility validation

- Document management and verification

- Notifications and status tracking

- Basic reporting for program oversight

### What's Included in MVP

✅ User Management & Authentication
✅ Case Management (Application to Approval)
✅ Document Management
✅ Notification System
✅ Basic Provider Registry
✅ Reporting Dashboard
✅ System Administration

### What's Deferred to Phase 2

⏭️ Full Provider Registration Workflow
⏭️ Attendance Tracking (Check-in/Check-out)
⏭️ Payment Calculation & Processing
⏭️ Financial System Integration
⏭️ Mobile Applications
⏭️ Advanced Analytics & Fraud Detection

## 🎯 PROJECT OBJECTIVES & SUCCESS METRICS

### Business Objectives

- Reduce Application Processing Time: From 30 days to 7 days (77% reduction)

- Increase Application Completion Rate: From 60% to 85%

- Improve Transparency: 100% of applicants can track status online

- Reduce Manual Data Entry: 90% automation of eligibility checks

- Enable Scalability: Handle 10,000+ applications per month

### Success Metrics (KPIs)

| Metric | Baseline | Target | Measurement |
| --- | --- | --- | --- |
| Average Application Processing Time | 30 days | 7 days | System timestamps |
| Application Completion Rate | 60% | 85% | Completed vs. Started |
| User Satisfaction Score | N/A | 4.0+/5.0 | Post-submission survey |
| System Uptime | N/A | 99.5% | Monitoring tools |
| Document Upload Success Rate | N/A | 95% | Upload vs. Errors |
| Caseworker Productivity | 5 cases/day | 15 cases/day | Cases processed |
| Parent Self-Service Rate | 0% | 80% | Status checks online |

## 👥 TEAM STRUCTURE

### Core Team (8-10 people)

#### Management & Leadership

- 1 Project Manager (100%) - Overall project coordination

- 1 Product Owner (50%) - Requirements, prioritization, UAT

- 1 Scrum Master (50%) - Agile ceremonies, impediment removal

#### Development Team

- 2 Full-Stack Developers (100%) - Backend + Frontend

- 1 Frontend Developer (100%) - React UI, accessibility

- 1 Backend Developer (100%) - APIs, integrations

- 1 DevOps Engineer (50%) - Infrastructure, CI/CD, deployment

#### Quality & Design

- 1 QA Engineer (100%) - Testing, quality assurance

- 1 UI/UX Designer (50%) - Wireframes, mockups, user testing

#### Subject Matter Experts (Part-time)

- 2-3 Program SMEs (20%) - Business rules, workflows

- 1 Security/Compliance SME (20%) - Security review

- 1 DBA (25%) - Database design and optimization

### Extended Team (As Needed)

- Cloud architect (consultant, 40 hours)

- Integration specialist (consultant, 80 hours)

- Technical writer (consultant, 80 hours)

## 📅 DETAILED 18-WEEK TIMELINE

### Phase 0: Project Initiation (Week 1)

#### Week 1: Project Kickoff & Setup

Duration: 5 days
Team: Full team

Activities:

- [ ] Project kickoff meeting

- [ ] Team onboarding and role clarification

- [ ] Development environment setup

- [ ] Cloud infrastructure provisioning (dev, test, staging)

- [ ] Project management tools setup (Jira/Linear)

- [ ] Communication channels setup (Slack/Teams)

- [ ] Code repository creation (GitHub/GitLab)

- [ ] CI/CD pipeline initial setup

Deliverables:

- ✅ Project Charter (signed)

- ✅ Team roster with contact info

- ✅ Development environment guide

- ✅ Git branching strategy

- ✅ Communication plan

Key Milestone: M1 - Project Kickoff Complete

### Phase 1: Requirements & Design (Weeks 2-4)

#### Week 2: Requirements Elaboration

Duration: 5 days
Focus: Detailed requirements gathering

Activities:

- [ ] Day 1-2: Conduct stakeholder workshops

  - Case management workflow mapping

  - Eligibility rules documentation

  - Document types and validation rules

  - Approval process definition

- [ ] Day 3: User role definition workshop

  - Define all user roles and permissions

  - Create permissions matrix

  - Map user journeys for each role

- [ ] Day 4: Integration requirements gathering

  - Identify authentication system (SSO or custom)

  - Document storage solution (AWS S3/Azure)

  - Email/SMS service providers

  - Government ID verification (if needed)

- [ ] Day 5: Non-functional requirements workshop

  - Performance requirements (load times, concurrent users)

  - Security requirements (encryption, audit logging)

  - Accessibility requirements (WCAG 2.1 AA)

  - Browser/device support matrix

Deliverables:

- ✅ Detailed Requirements Document (DRD)

- ✅ User Stories Backlog (100+ stories)

- ✅ Eligibility Rules Specification

- ✅ Document Requirements Matrix

- ✅ Integration Specifications

- ✅ Non-Functional Requirements (NFR) Document

Key Milestone: M2 - Requirements Sign-Off

#### Week 3: Technical Design

Duration: 5 days
Focus: Architecture, database, and API design

Activities:

- [ ] Day 1: Solution architecture design

  - High-level architecture diagram

  - Technology stack finalization

  - Deployment architecture

  - Security architecture

- [ ] Day 2-3: Database design

  - Entity-relationship diagram (ERD)

  - Database schema (all tables, relationships)

  - Data dictionary

  - Migration strategy

- [ ] Day 4: API design

  - RESTful API endpoint design

  - Request/response formats

  - Authentication/authorization flow

  - API documentation (OpenAPI/Swagger)

- [ ] Day 5: Integration architecture

  - Integration points mapping

  - Data flow diagrams

  - Error handling strategy

  - Retry and fallback mechanisms

Deliverables:

- ✅ Solution Architecture Document

- ✅ Database Schema (SQL scripts)

- ✅ ERD Diagram

- ✅ API Specification (OpenAPI)

- ✅ Integration Design Document

- ✅ Security Design Document

#### Week 4: UI/UX Design & Sprint Planning

Duration: 5 days
Focus: User interface design and development preparation

Activities:

- [ ] Day 1-2: Wireframing

  - Parent application flow

  - Caseworker review dashboard

  - Admin configuration screens

  - Mobile-responsive layouts

- [ ] Day 3-4: Visual design

  - Design system creation

  - Component library

  - High-fidelity mockups

  - Accessibility review

- [ ] Day 5: Sprint planning

  - Story estimation (planning poker)

  - Sprint 1-7 roadmap

  - Release planning

  - Risk assessment update

Deliverables:

- ✅ Complete Wireframes (30+ screens)

- ✅ High-Fidelity Mockups (key screens)

- ✅ Design System / Style Guide

- ✅ Sprint Roadmap

- ✅ Product Backlog (prioritized)

Key Milestone: M3 - Design Approved, Ready for Development

### Phase 2: Development Sprints (Weeks 5-14)

#### Sprint 1 (Weeks 5-6): Foundation & User Management

Duration: 2 weeks
Sprint Goal: Working authentication and user management system

User Stories (Priority: MUST HAVE):

- As a Parent, I want to register for an account, so I can apply for assistance

- As a Caseworker, I want to log in securely, so I can access cases

- As an Admin, I want to manage user roles, so I can control access

- As a User, I want to reset my password, so I can recover my account

- As a System, I want to log all user actions, so we maintain audit trail

Technical Tasks:

- [ ] Set up database and migrations

- [ ] Implement authentication (JWT or SSO)

- [ ] Build user registration API

- [ ] Build user login API

- [ ] Implement RBAC (Role-Based Access Control)

- [ ] Create user management API endpoints

- [ ] Build React user registration form

- [ ] Build login page

- [ ] Build password reset flow

- [ ] Implement session management

- [ ] Set up audit logging

- [ ] Write unit tests (80% coverage)

- [ ] Write integration tests

Deliverables:

- ✅ Working authentication system

- ✅ User registration flow

- ✅ Role-based access control

- ✅ User management dashboard (admin)

- ✅ Unit tests + integration tests

Definition of Done:

- All acceptance criteria met

- Code reviewed and approved

- Unit test coverage ≥ 80%

- Integration tests passing

- Deployed to test environment

- UAT ready

#### Sprint 2 (Weeks 7-8): Document Management

Duration: 2 weeks
Sprint Goal: Secure document upload and management system

User Stories:

- As a Parent, I want to upload documents securely, so I can submit proof of income

- As a Caseworker, I want to view uploaded documents, so I can verify eligibility

- As a System, I want to scan documents for viruses, so we maintain security

- As a Parent, I want to see my uploaded documents, so I can track what I've submitted

- As an Admin, I want to configure document types, so we require the right documents

Technical Tasks:

- [ ] Set up cloud storage (AWS S3 or Azure Blob)

- [ ] Implement file upload API with virus scanning

- [ ] Build document metadata storage (database)

- [ ] Implement document retrieval API

- [ ] Build document viewer (in-browser, secure)

- [ ] Implement document categorization

- [ ] Build document upload UI component

- [ ] Build document library UI

- [ ] Implement file type validation

- [ ] Implement file size limits

- [ ] Add document status tracking

- [ ] Write unit and integration tests

Deliverables:

- ✅ Document upload functionality

- ✅ Secure document storage

- ✅ Document viewer

- ✅ Document management dashboard

- ✅ Admin document type configuration

#### Sprint 3 (Weeks 9-10): Case Management - Application Submission

Duration: 2 weeks
Sprint Goal: Parents can submit complete applications online

User Stories:

- As a Parent, I want to fill out an application online, so I can apply for assistance

- As a Parent, I want to save a draft application, so I can complete it later

- As a Parent, I want to upload required documents, so I can submit proof

- As a Parent, I want to review my application before submission, so I can check for errors

- As a System, I want to validate application data, so we ensure data quality

Technical Tasks:

- [ ] Design case/application database tables

- [ ] Build application submission API

- [ ] Build application draft save/load API

- [ ] Implement data validation rules

- [ ] Build multi-step application form (React)

- [ ] Integrate document upload in application flow

- [ ] Build application review/summary page

- [ ] Implement form auto-save

- [ ] Build application submission confirmation

- [ ] Add email notification on submission

- [ ] Write comprehensive tests

Form Sections:

- Personal Information (name, DOB, SSN, address, phone, email)

- Household Information (household size, dependents)

- Employment Information (employer, income, work schedule)

- Child Information (name, DOB, special needs)

- Provider Selection (choose from registered providers)

- Document Upload (income proof, employment verification, child documents)

- Certification and Signature

Deliverables:

- ✅ Multi-step application form

- ✅ Draft save functionality

- ✅ Document integration

- ✅ Application submission workflow

- ✅ Confirmation page and email

#### Sprint 4 (Weeks 11-12): Case Management - Eligibility & Review

Duration: 2 weeks
Sprint Goal: Automated eligibility check and caseworker review workflow

User Stories:

- As a System, I want to check eligibility automatically, so we reduce manual work

- As a Caseworker, I want to see my assigned cases, so I know what to review

- As a Caseworker, I want to view application details, so I can evaluate eligibility

- As a Caseworker, I want to view uploaded documents, so I can verify information

- As a Caseworker, I want to add case notes, so I can document my review

Technical Tasks:

- [ ] Build eligibility rules engine

- [ ] Implement income threshold validation

- [ ] Implement work requirement validation

- [ ] Build case assignment logic

- [ ] Build caseworker dashboard API

- [ ] Build case detail view API

- [ ] Build case notes API

- [ ] Build caseworker dashboard UI

- [ ] Build case review page UI

- [ ] Build case notes interface

- [ ] Implement case status workflow

- [ ] Write tests for eligibility rules

Eligibility Rules (Configurable):

- Income threshold: ≤ 200% of Federal Poverty Level (FPL)

- Employment requirement: Working ≥ 20 hours/week OR in school/training

- Residency: State resident

- Child age: 0-13 years (or up to 18 if special needs)

- Citizenship: U.S. citizen or qualified immigrant

- Provider: Must select licensed provider

Deliverables:

- ✅ Automated eligibility validation

- ✅ Caseworker dashboard

- ✅ Case review interface

- ✅ Case notes functionality

- ✅ Case assignment workflow

#### Sprint 5 (Weeks 13-14): Case Management - Approval & Notifications

Duration: 2 weeks
Sprint Goal: Caseworkers can approve/reject cases, parents receive notifications

User Stories:

- As a Caseworker, I want to approve applications, so eligible families get assistance

- As a Caseworker, I want to reject applications with reasons, so parents understand why

- As a Parent, I want to receive email notifications, so I know my application status

- As a Parent, I want to check my application status online, so I can track progress

- As a System, I want to send automated reminders, so applications don't stall

Technical Tasks:

- [ ] Build approval/rejection API

- [ ] Implement rejection reason codes

- [ ] Build notification service integration

- [ ] Set up email service (SendGrid/AWS SES)

- [ ] Set up SMS service (Twilio/AWS SNS) - optional

- [ ] Create notification templates

- [ ] Build approval/rejection UI

- [ ] Build parent status dashboard

- [ ] Implement notification history

- [ ] Build notification preferences

- [ ] Implement automated reminders

- [ ] Write comprehensive tests

Notification Templates:

- Application Received

- Application Under Review

- Additional Information Required

- Application Approved

- Application Rejected

- Document Upload Reminder

- Renewal Reminder (future)

Deliverables:

- ✅ Approval/rejection workflow

- ✅ Email notification system

- ✅ SMS notifications (optional)

- ✅ Parent status dashboard

- ✅ Notification templates and preferences

Key Milestone: M4 - Core Case Management Complete

#### Sprint 6 (Weeks 15-16): Reporting & Basic Provider Registry

Duration: 2 weeks
Sprint Goal: Reporting dashboard and basic provider lookup

User Stories:

- As a Manager, I want to see application volume reports, so I understand workload

- As a Manager, I want to see approval rates, so I can monitor program performance

- As a Caseworker, I want to see my productivity metrics, so I can track my work

- As a Parent, I want to search for providers, so I can choose childcare

- As an Admin, I want to manage provider listings, so parents see current providers

Technical Tasks:

Reporting:

- [ ] Design reporting database schema

- [ ] Build report generation API

- [ ] Build dashboard API endpoints

- [ ] Implement report filters

- [ ] Build executive dashboard UI

- [ ] Build caseworker dashboard UI

- [ ] Implement data export (CSV, PDF)

- [ ] Build report scheduling

Provider Registry:

- [ ] Design provider database tables

- [ ] Import existing licensed providers (data migration)

- [ ] Build provider search API

- [ ] Build provider detail API

- [ ] Build provider search UI

- [ ] Build provider detail page

- [ ] Build admin provider management UI

Reports to Build:

- Application Volume by County/Month

- Approval/Rejection Rate by Reason

- Average Processing Time

- Case Status Summary

- Caseworker Productivity

- Pending Cases Report

- Document Verification Status

Deliverables:

- ✅ Reporting dashboard

- ✅ 7 standard reports

- ✅ Data export functionality

- ✅ Provider search and directory

- ✅ Admin provider management

#### Sprint 7 (Weeks 17-18): System Admin & Polish

Duration: 2 weeks
Sprint Goal: System administration tools and final polish

User Stories:

- As an Admin, I want to configure eligibility rules, so we can adjust thresholds

- As an Admin, I want to manage reference data, so the system stays current

- As an Admin, I want to view system logs, so I can troubleshoot issues

- As an Admin, I want to manage announcement banners, so I can communicate updates

- As a User, I want an accessible system, so everyone can use it

Technical Tasks:

- [ ] Build system configuration API

- [ ] Build reference data management API

- [ ] Build system configuration UI

- [ ] Build reference data management UI

- [ ] Build system monitoring dashboard

- [ ] Build log viewer

- [ ] Implement feature flags

- [ ] Build announcement banner system

- [ ] Conduct accessibility audit (WCAG 2.1 AA)

- [ ] Fix accessibility issues

- [ ] Conduct security audit

- [ ] Fix security vulnerabilities

- [ ] Performance optimization

- [ ] Bug fixing and polish

Reference Data to Manage:

- Income thresholds (by household size)

- County/region list

- Rejection reason codes

- Document types required

- Work hour requirements

- Age limits

- Provider types

- Notification templates

Deliverables:

- ✅ System administration console

- ✅ Reference data management

- ✅ System monitoring dashboard

- ✅ WCAG 2.1 AA compliance

- ✅ Security hardening

- ✅ Performance optimization

Key Milestone: M5 - Development Complete

### Phase 3: Testing & Quality Assurance (Weeks 15-18, parallel with Sprints 6-7)

#### Continuous Testing Activities

Unit Testing (Ongoing):

- Target: 80% code coverage

- Automated in CI/CD pipeline

- Run on every commit

Integration Testing (Weekly):

- API endpoint testing

- Database integration testing

- Third-party service integration

- End-to-end workflow testing

Performance Testing (Week 16):

- Load testing (1000 concurrent users)

- Stress testing (peak load scenarios)

- Endurance testing (24-hour run)

- Database query optimization

Security Testing (Week 17):

- Vulnerability scanning (OWASP Top 10)

- Penetration testing

- Authentication/authorization testing

- Data encryption verification

- Audit logging verification

Accessibility Testing (Week 17-18):

- Screen reader testing (JAWS, NVDA, VoiceOver)

- Keyboard navigation testing

- Color contrast verification

- ARIA label verification

- WCAG 2.1 AA compliance checklist

Browser/Device Testing (Week 18):

- Desktop browsers: Chrome, Firefox, Safari, Edge (latest 2 versions)

- Mobile browsers: iOS Safari, Chrome Mobile

- Tablet testing: iPad, Android tablet

- Responsive design verification

Test Deliverables:

- ✅ Test plan document

- ✅ Test cases (500+ test cases)

- ✅ Automated test suite

- ✅ Performance test report

- ✅ Security audit report

- ✅ Accessibility audit report

- ✅ Defect log and resolution report

### Phase 4: User Acceptance Testing (Weeks 19-20)

#### Week 19: UAT Preparation

Duration: 5 days

Activities:

- [ ] UAT environment setup

- [ ] Test data preparation

- [ ] UAT user training (4-hour session)

- [ ] UAT test case distribution

- [ ] UAT kickoff meeting

UAT Participants:

- 5 Parents (representing different demographics)

- 5 Caseworkers (from different counties)

- 2 Program Managers

- 1 IT Admin

#### Week 20: UAT Execution

Duration: 5 days

Test Scenarios:

Parent Scenarios:

- Register new account

- Complete full application

- Upload documents

- Save draft and resume later

- Check application status

- Respond to information request

Caseworker Scenarios:

- Log in and view dashboard

- Review new application

- Verify documents

- Add case notes

- Approve application

- Reject application with reason

- Generate reports

Admin Scenarios:

- Create new caseworker account

- Configure eligibility thresholds

- Manage provider listings

- View system reports

- Manage reference data

UAT Success Criteria:

- 90% of test scenarios pass

- No critical defects

- < 5 high-priority defects

- User satisfaction score ≥ 4.0/5.0

- All accessibility tests pass

UAT Deliverables:

- ✅ UAT test execution report

- ✅ User feedback summary

- ✅ Defect list and prioritization

- ✅ UAT sign-off document

Key Milestone: M6 - UAT Sign-Off

### Phase 5: Pre-Production (Weeks 21-22)

#### Week 21: Production Environment Setup

Duration: 5 days

Activities:

- [ ] Production infrastructure provisioning

- [ ] Production database setup

- [ ] SSL certificate installation

- [ ] Security hardening

- [ ] Monitoring and alerting setup (CloudWatch, Datadog)

- [ ] Backup configuration

- [ ] Disaster recovery testing

- [ ] Performance testing in prod-like environment

- [ ] Load balancer configuration

- [ ] CDN configuration (for static assets)

Infrastructure Setup:

- Application Servers: Auto-scaling group (min 2, max 10 instances)

- Database: RDS PostgreSQL (Multi-AZ, automated backups)

- Storage: S3 with encryption at rest

- CDN: CloudFront for static assets

- Monitoring: CloudWatch + Datadog dashboards

- Logging: Centralized logging (CloudWatch Logs or ELK stack)

#### Week 22: Data Migration & Final Testing

Duration: 5 days

Activities:

- [ ] Day 1-2: Data migration preparation

  - Export existing provider data

  - Data cleansing and validation

  - Data mapping verification

  - Dry run migration

- [ ] Day 3: Production data migration

  - Migrate provider directory

  - Migrate user accounts (if any)

  - Data validation and reconciliation

- [ ] Day 4: Smoke testing in production

  - Test all critical paths

  - Test integrations

  - Test notifications

  - Test performance

- [ ] Day 5: Go-live preparation

  - Deploy monitoring dashboards

  - Brief support team

  - Set up war room

  - Final go/no-go meeting

Deliverables:

- ✅ Production environment ready

- ✅ Data migration complete

- ✅ Smoke tests passing

- ✅ Monitoring operational

- ✅ Support team trained

- ✅ Go-live runbook

Key Milestone: M7 - Production Ready

### Phase 6: Deployment & Go-Live (Week 23)

#### Week 23: Go-Live Week

Duration: 5 days

Go-Live Strategy: Phased rollout by county

Day 1 (Monday): Soft launch

- Deploy to production

- Open to pilot county only (100-200 users)

- Intensive monitoring (war room)

- Support team on standby

Day 2 (Tuesday): Monitor and stabilize

- Monitor all metrics

- Fix any critical issues

- Gather user feedback

- Performance monitoring

Day 3 (Wednesday): Expand to 3 more counties

- If stable, expand access

- Continue monitoring

- Support team responds to issues

Day 4 (Thursday): Full statewide rollout

- Open to all counties

- Marketing/communication push

- Help desk fully staffed

Day 5 (Friday): Stabilization

- Monitor system stability

- Address any issues

- Collect feedback

- Plan for week 2 improvements

War Room Schedule:

- Days 1-3: 24/7 coverage

- Days 4-7: Extended hours (6 AM - 10 PM)

- Week 2+: Business hours support

Go-Live Checklist:

- [ ] All production services running

- [ ] Monitoring dashboards operational

- [ ] Support team briefed and ready

- [ ] Communication sent to all stakeholders

- [ ] Help desk phone lines open

- [ ] Rollback plan ready (if needed)

- [ ] Backup verified (last 24 hours)

- [ ] Performance baseline established

- [ ] Go-live approval from Project Sponsor

Key Milestone: M8 - System Go-Live

### Phase 7: Hypercare & Stabilization (Weeks 24-26)

#### Weeks 24-26: Post-Launch Support

Duration: 3 weeks

Activities:

- [ ] Daily: Monitor system health and performance

- [ ] Daily: Review support tickets and resolve issues

- [ ] Daily: Track KPIs and user adoption

- [ ] Weekly: User feedback analysis

- [ ] Weekly: Bug triage and fixing

- [ ] Weekly: Performance optimization

- [ ] End of Period: Lessons learned session

- [ ] End of Period: Project closure report

- [ ] End of Period: Transition to operations team

Support Model:

- Week 1 (Week 24): Development team on standby (response time: 1 hour)

- Week 2 (Week 25): Development team available (response time: 4 hours)

- Week 3 (Week 26): Handoff to operations (response time: 24 hours)

Monitoring & Metrics:

- System uptime (target: 99.5%)

- Page load times (target: < 2 seconds)

- API response times (target: < 500ms)

- Error rates (target: < 1%)

- Application completion rate (target: 85%)

- Average processing time (target: < 7 days)

- User satisfaction score (target: 4.0+/5.0)

Deliverables:

- ✅ Daily status reports

- ✅ Issue resolution log

- ✅ Performance reports

- ✅ User adoption metrics

- ✅ Lessons learned document

- ✅ Project closure report

- ✅ Operations handoff complete

Key Milestone: M9 - Project Complete, Operations Transition

## 💰 BUDGET BREAKDOWN

### Total Budget: $650,000 - $800,000

#### Personnel Costs (26 weeks): $520,000

| Role | Rate | Weeks | % Time | Cost |
| --- | --- | --- | --- | --- |
| Project Manager | $8,000/wk | 26 | 100% | $208,000 |
| Product Owner | $7,000/wk | 26 | 50% | $91,000 |
| Scrum Master | $6,000/wk | 26 | 50% | $78,000 |
| Full-Stack Developer (2) | $8,000/wk | 22 | 100% | $352,000 |
| Frontend Developer | $7,500/wk | 22 | 100% | $165,000 |
| Backend Developer | $8,000/wk | 22 | 100% | $176,000 |
| DevOps Engineer | $8,500/wk | 26 | 50% | $110,500 |
| QA Engineer | $6,500/wk | 22 | 100% | $143,000 |
| UI/UX Designer | $7,000/wk | 8 | 50% | $28,000 |
| Subtotal |  |  |  | $1,351,500 |

#### Adjusted Personnel (Realistic Team Size)

| Role | Rate | Weeks | % Time | Cost |
| --- | --- | --- | --- | --- |
| Project Manager | $8,000/wk | 26 | 100% | $208,000 |
| Full-Stack Developer (2) | $8,000/wk | 22 | 100% | $176,000 |
| QA Engineer | $6,500/wk | 22 | 100% | $143,000 |
| UI/UX Designer | $7,000/wk | 8 | 50% | $28,000 |
| DevOps (Consultant) | $200/hr | 160 hrs |  | $32,000 |
| Adjusted Subtotal |  |  |  | $587,000 |

#### Infrastructure & Tools: $45,000

| Item | Annual Cost | 6 Months | Notes |
| --- | --- | --- | --- |
| Cloud Hosting (AWS/Azure) | $36,000 | $18,000 | Dev + Test + Staging + Prod |
| CI/CD Tools | $1,200 | $600 | GitHub Actions, Jenkins |
| Monitoring (Datadog) | $6,000 | $3,000 | Full stack monitoring |
| Project Management (Jira) | $1,200 | $600 | 15 users |
| Design Tools (Figma) | $900 | $450 | 3 users |
| Communication (Slack) | $1,200 | $600 | Team plan |
| Documentation (Confluence) | $1,200 | $600 | Team wiki |
| Email Service (SendGrid) | $1,200 | $600 | 50K emails/month |
| SMS Service (Twilio) | $2,400 | $1,200 | 10K SMS/month |
| Storage (S3) | $2,400 | $1,200 | 5TB storage |
| Database (RDS) | $12,000 | $6,000 | PostgreSQL Multi-AZ |
| Security Tools | $3,600 | $1,800 | Vulnerability scanning |
| Subtotal |  | $34,650 |  |

#### AI Tools: $600

| Tool | Cost/User | Users | 6 Months | Total |
| --- | --- | --- | --- | --- |
| GitHub Copilot | $19/mo | 4 | 6 | $456 |
| Claude Pro | $20/mo | 2 | 6 | $240 |
| v0.dev | $20/mo | 1 | 3 | $60 |
| Subtotal |  |  |  | $756 |

#### Consulting & Services: $30,000

- Cloud architect (40 hours @ $250/hr): $10,000

- Security consultant (40 hours @ $250/hr): $10,000

- Technical writer (80 hours @ $125/hr): $10,000

#### Contingency (10%): $65,000

### TOTAL MVP BUDGET: $717,406

### Cost Savings vs. Traditional Approach

- Traditional Approach: $1.2M - $1.5M (42 weeks, larger team)

- AI-Assisted MVP: $717K (26 weeks, smaller team)

- Savings: $483K - $783K (40-52%)

## 🎯 QUALITY ASSURANCE PLAN

### Code Quality Standards

Code Reviews:

- All code must be reviewed by at least one other developer

- No direct commits to main branch

- Pull request template with checklist

- Automated linting (ESLint, Prettier)

Testing Requirements:

- Unit test coverage ≥ 80%

- All critical paths have integration tests

- E2E tests for main user workflows

- Accessibility tests for all UI components

Performance Standards:

- Page load time: < 2 seconds (95th percentile)

- API response time: < 500ms (95th percentile)

- Database query time: < 100ms (average)

- Support 1000 concurrent users

Security Standards:

- No high or critical vulnerabilities

- All data encrypted in transit (TLS 1.3)

- All sensitive data encrypted at rest

- Password policy enforced (12+ chars, complexity)

- Session timeout: 30 minutes inactivity

- Complete audit logging

Accessibility Standards:

- WCAG 2.1 Level AA compliance

- Keyboard navigation functional

- Screen reader compatible

- Color contrast ratio ≥ 4.5:1

- ARIA labels properly implemented

## 📊 RISK MANAGEMENT

### Top 10 Risks & Mitigation Strategies

| # | Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| 1 | Requirements change during development | Medium | High | Agile approach, change control process, buffer in timeline |
| 2 | Integration with external systems delayed | Medium | High | Early integration testing, mock services, fallback plans |
| 3 | Security vulnerabilities discovered | Low | Critical | Regular security scans, penetration testing, security reviews |
| 4 | Performance issues at scale | Medium | High | Early load testing, performance monitoring, optimization sprints |
| 5 | Data migration issues | Medium | High | Multiple dry runs, validation scripts, rollback plan |
| 6 | Key team member leaves | Low | High | Knowledge sharing, documentation, cross-training |
| 7 | UAT reveals major usability issues | Medium | Medium | Early user testing, iterative design, regular stakeholder demos |
| 8 | Cloud infrastructure costs exceed budget | Low | Medium | Cost monitoring, resource optimization, reserved instances |
| 9 | Accessibility compliance issues | Medium | Medium | Early accessibility testing, expert review, remediation time |
| 10 | Go-live disrupts existing operations | Medium | High | Phased rollout, comprehensive training, 24/7 support |

### Risk Response Plans

For High-Impact Risks:

- Weekly risk review in sprint retrospectives

- Escalation path defined

- Contingency budget allocated

- Alternative approaches identified

## 📋 COMMUNICATION PLAN

### Stakeholder Communication Matrix

| Stakeholder | Frequency | Method | Content |
| --- | --- | --- | --- |
| Project Sponsor | Weekly | Email + Meeting | Status, risks, decisions needed |
| Steering Committee | Bi-weekly | Presentation | Progress, budget, timeline |
| End Users (Parents) | As needed | Email, SMS | System updates, training |
| Caseworkers | Weekly | Email, Training | New features, tips, support |
| Development Team | Daily | Standup | Progress, blockers, plan |
| QA Team | Daily | Slack | Test results, defects |
| IT Operations | Weekly | Meeting | Infrastructure, performance |

### Status Reporting

Weekly Status Report (Every Friday):

- Accomplishments this week

- Plan for next week

- Risks and issues

- Budget status

- Timeline status

- Decisions needed

Sprint Demo (Every 2 weeks):

- Live demo of new features

- Stakeholder feedback

- Adjustments for next sprint

Monthly Executive Summary:

- High-level progress

- Key metrics

- Budget variance

- Timeline variance

- Major risks

## 🎓 TRAINING PLAN

### Training Schedule

#### Week 21: Caseworker Training

Duration: 4 hours
Format: In-person or virtual workshop
Participants: All caseworkers (50-100 people)

Topics:

- System overview and navigation (30 min)

- Case review workflow (60 min)

- Document verification (30 min)

- Approval/rejection process (30 min)

- Reporting and productivity tools (30 min)

- Q&A and hands-on practice (60 min)

Materials:

- User manual (PDF)

- Video tutorials (10 short videos)

- Quick reference guide

- Practice environment access

#### Week 22: Parent Onboarding

Format: Self-service + help desk
Materials:

- Welcome email with getting started guide

- Video: "How to apply in 5 steps" (5 min)

- FAQ page

- Live chat support

- Phone support hotline

#### Week 22: Admin Training

Duration: 2 hours
Format: In-person workshop
Participants: System administrators (5-10 people)

Topics:

- System configuration (30 min)

- User management (20 min)

- Reference data management (20 min)

- Monitoring and troubleshooting (30 min)

- Backup and recovery (20 min)

## 🚀 GO-LIVE READINESS CHECKLIST

### Production Readiness (Week 22)

#### Technical Readiness

- [ ] All production infrastructure provisioned

- [ ] Production database configured and tested

- [ ] All integrations tested in production

- [ ] SSL certificates installed and verified

- [ ] Monitoring and alerting configured

- [ ] Backup and disaster recovery tested

- [ ] Performance testing completed

- [ ] Security audit passed

- [ ] Accessibility audit passed

- [ ] Load testing passed (1000+ concurrent users)

#### Data Readiness

- [ ] Provider directory migrated

- [ ] User accounts migrated (if applicable)

- [ ] Reference data loaded (counties, thresholds)

- [ ] Data validation completed

- [ ] Data reconciliation report approved

#### Documentation Readiness

- [ ] User manuals completed

- [ ] Admin guide completed

- [ ] API documentation completed

- [ ] Training materials completed

- [ ] FAQ populated

- [ ] Help articles published

- [ ] Video tutorials published

#### Support Readiness

- [ ] Help desk staffed and trained

- [ ] Support phone lines active

- [ ] Support email monitored

- [ ] Live chat configured

- [ ] Escalation procedures documented

- [ ] War room schedule confirmed

- [ ] On-call rotation established

#### Stakeholder Readiness

- [ ] All training sessions completed

- [ ] Communication sent to all users

- [ ] Provider outreach completed

- [ ] Parent communication sent

- [ ] Media/PR coordinated (if applicable)

- [ ] Steering committee approval obtained

- [ ] Executive sponsor sign-off obtained

#### Operational Readiness

- [ ] Go-live runbook reviewed

- [ ] Rollback plan documented and tested

- [ ] Go/No-Go criteria defined

- [ ] Go/No-Go meeting scheduled

- [ ] Post-launch support plan confirmed

- [ ] Issue triage process established

- [ ] Performance baseline established

## 📈 POST-LAUNCH SUCCESS METRICS

### Week 1 Metrics (Critical)

- System uptime: 99.5%+

- Error rate: < 1%

- Page load time: < 2 seconds

- API response time: < 500ms

- Support ticket resolution: < 4 hours

### Month 1 Metrics (Important)

- Parent registrations: 500+ accounts

- Applications submitted: 300+ applications

- Applications approved: 200+ approvals

- Average processing time: < 10 days (improving to 7)

- User satisfaction: 3.5+/5.0 (improving to 4.0)

- Support ticket volume: Decreasing weekly

### Month 3 Metrics (Success Indicators)

- Parent registrations: 2,000+ accounts

- Applications submitted: 1,500+ applications

- Application completion rate: 75%+

- Average processing time: < 7 days (target achieved)

- User satisfaction: 4.0+/5.0 (target achieved)

- Caseworker productivity: 12+ cases/day

- System uptime: 99.7%+

## 🎯 DEFINITION OF SUCCESS

The MVP is considered successful if:

- ✅ Deployed on time: Launched within 26 weeks

- ✅ Within budget: < $800K total cost

- ✅ Functional: All MVP features working as specified

- ✅ Quality: No critical defects, < 10 high-priority defects

- ✅ Performance: Meets all performance SLAs

- ✅ Security: Passed security audit, no high vulnerabilities

- ✅ Accessible: WCAG 2.1 AA compliant

- ✅ Adopted: 500+ parents registered in first month

- ✅ Efficient: Average processing time < 10 days (month 1)

- ✅ Satisfying: User satisfaction ≥ 3.5/5.0 (month 1)

## 📚 DELIVERABLES SUMMARY

### Documentation Deliverables

- Detailed Requirements Document

- Solution Architecture Document

- Database Schema & ERD

- API Documentation (OpenAPI)

- User Manuals (by role)

- Admin Guide

- Training Materials

- Test Plan & Test Cases

- Security Audit Report

- Performance Test Report

- UAT Report & Sign-off

- Go-Live Runbook

- Operations Manual

- Project Closure Report

### Technical Deliverables

- Working MVP Application (production)

- Source code repository

- Automated test suite

- CI/CD pipeline

- Infrastructure as Code (IaC)

- Monitoring dashboards

- Backup & DR procedures

## 🔄 NEXT STEPS AFTER MVP

### Phase 2 Planning (Weeks 27-28)

- Gather feedback from MVP users

- Prioritize Phase 2 features

- Plan Provider Management module

- Plan Attendance Tracking module

- Budget approval for Phase 2

### Phase 2: Provider Management & Attendance (10 weeks)

- Full provider registration workflow

- Provider verification by state

- Attendance tracking (check-in/check-out)

- QR code / PIN entry system

- Attendance reporting

- Attendance anomaly detection

### Phase 3: Finance & Payments (8 weeks)

- Payment calculation engine

- Payment approval workflow

- ACH/banking integration

- Payment reconciliation

- Financial reporting

## 📞 PROJECT CONTACTS

### Project Leadership

- Project Sponsor: [Name, Title, Email, Phone]

- Project Manager: [Name, Email, Phone]

- Product Owner: [Name, Email, Phone]

- Technical Lead: [Name, Email, Phone]

### Escalation Path

- Level 1: Scrum Master / Team Lead

- Level 2: Project Manager

- Level 3: Program Director

- Level 4: Project Sponsor / CIO

## ✅ CONCLUSION

This MVP Implementation Plan provides a comprehensive roadmap for delivering the Case Management System in 26 weeks with a budget of $650K-$800K.

Key Success Factors:

- Clear scope and requirements

- Experienced team with AI tools

- Agile methodology with governance

- Regular stakeholder engagement

- Comprehensive testing

- Phased, low-risk go-live

- Strong support model

Next Immediate Actions:

- Get this plan approved by steering committee

- Secure budget allocation

- Start team recruitment/assignment

- Begin Week 1: Project Kickoff

- Follow the detailed weekly schedule

Remember: This is an ambitious but achievable plan. Success requires commitment, discipline, and collaboration from all stakeholders.

Document Version: 1.0
Last Updated: November 8, 2025
Approved By: [Pending]
Next Review: After Week 4 (Design Approval)

Ready to start? Open DETAILED_REQUIREMENTS_SPECIFICATION.md next! 🚀 SCMS Detailed Requirements Specification